## Draft Conformance Delivery Proc
Phase | Activity | Task Detail | PT1 Principle | Deliverable | Owner | Quarter | Start Date | End Date | Status
Phase 1: Compliance Analysis and Prep | PT1 Breakdown & Control Mapping | Break down the CEN-CRA-PT1 principles into detailed, auditable control requirements (similar to how we map ISO/SOC controls and focused on what evidence is needed for each). | 1. Security by Design | Detailed PT1 Control Matrix (Internal mapping) | PSC | Q4 2025 | 2025-10-01 | 2025-12-31 | Started
Phase 1: Compliance Analysis and Prep | Evidence Gathering | For each control, define the necessary evidence (e.g., ComplyTime, documentation, Jira ticket closures, etc.). Determine the Source: Identify if the evidence resides in Konflux, Jira, or another system. | All Principles (Evidence Sourcing) | CRA Evidence Sourcing Plan (coordinated with Automation Plan) | PSC | Q1 2026 | 2026-01-01 | 2026-03-31 | Started
Phase 1: Compliance Analysis and Prep | Documentation Analysis | 1. Identify what documentation is required as part of conformance. Determine what of that documentation MUST be publically released with the conformance statment, and what documentation is not required to be publically released but rather retained on hand for audit. 2. Gap analysis (how much of documentation already exists, what is the gap). 3. Define the centralized, internal and external documentation solution (Customer Portal, specialized hub) 4. Strategy for ensuring all documentation maintains consistent look and feel across all products. | All Principles (Transparency) | 1. Documentation release analysis 2. Documentation Gap Analysis 3. Final Repository 4. Strategy for consistent look and feel (template) 5. List of applicable documents (wiki?) | PSC | Q2 2026 | 2026-04-01 | 2026-06-30 | Not Started
Phase 1: Compliance Analysis and Prep | Third party assessment vendors onboarded | Begin initial outreach to potential CRA vendors for potential assessors. | All Principles (External Validation) | Approved list of 3PAOs | PSC | Q3 2026 | 2026-07-01 | 2026-09-30 | Started
Phase 1: Compliance Analysis and Prep | Third party test labs onboarded | Begin initial outreach to potential test labs for potential assessors. (research extending Common Criteria relationships to include CRA). | All Principles (External Validation) | Approved list of test labs | PSC | Q3 2026 | 2026-07-01 | 2026-09-30 | Started
Phase 2: Automation and Tooling | Automation plan | Analyse and plan the automated evidence retrieval process (i.e. Konflux, other sources). How will the final system retrieve the evidence? Prioritize automation over manual retrieval for the vast majority of controls. | 1. Security by Design | Retrieval Automation Plan (maybe a diagram?) | PSC | Q2 2026 | 2026-04-01 | 2026-06-30 | Not Started
Phase 2: Automation and Tooling | Final Statement of Conformity Development | Create and vet the final Statement of Conformity (SoC) template to ensure legal compliance and consistent branding. | 1 & 2 (Compliance & Disclosure) | Standardized Statement of Conformity | PSC, Legal | Q2 2026 | 2026-04-01 | 2026-06-30 | Not Started
Phase 2: Automation and Tooling | Pilot Product Selection Target | Set a target date for selecting the initial easy-to-audit pilot product (e.g., uses Konflux, has good SDLC metrics, known team). | N/A (Project Governance) | Approved Target Pilot Selection Date | PSC | Q2 2026 | 2026-04-01 | 2026-06-30 | Not Started
Phase 3: Validation, and Readiness | Pilot Internal Audit | 1.Conduct an internal audit on execution of the conformance delivery process on the selected pilot product. 2. Document lessons learned and conduct 2 more pilots. | All Principles (Independent Assurance) | Internal Audit Execution Plan | PSC | Q3 2026 - Q4 2026 | 2026-07-01 | 2026-12-31 | Not Started
Phase 3: Validation, and Readiness | Final Process Mandate | Obtain formal sign-off mandating the use of the new Conformance Delivery Process for all in-scope products. | 1. Security by Design (Management Approval) | Signed Conformance Delivery Process (V1.0) | PSC | Q4 2026 | 2026-10-01 | 2026-12-31 | Not Started
Phase 4: Adoption and Outliers | Conformance Delivery Adopted Portfolio-wide | Majority (if not all) products released following the adopted conformance standards | Security by Design | Updated metrics on products released following the adopted process. | PSC | Q1 2027 | 46388 | 46477 | Not Started
Phase 4: Adoption and Outliers | Products not covered under conformance | Reach out to internal teams (e.g. sustatining engineering) to ensure all products meet conformance standards | All Principles | List of potential products not covered and plan to meet conformance standards | PSC | Q1 2027 | 46388 | 46477 | Not Started
Phase 5: Lifecycle management | PDS Solution (Standing up governance) |  |  |  | PSC | Q1 2026 - Q3 2026 | 46037 | 46295 | Not Started