## Draft Conformance Delivery Proc
Phase | Activity | Task Detail | PT1 Principle | Deliverable | Owner | Quarter | Start Date | End Date
Phase 1: Compliance Analysis and Prep | PT1 Breakdown & Control Mapping | Break down the CEN-CRA-PT1 principles into detailed, auditable control requirements (similar to how we map ISO/SOC controls and focused on what evidence is needed for each). | 1. Security by Design | Detailed PT1 Control Matrix (Internal mapping) | PSC | Q4 2025 | 2025-10-01 | 2025-12-31
Phase 1: Compliance Analysis and Prep | Evidence Gathering | For each control, define the necessary evidence (e.g., screen shots, documentation, Jira ticket closures). Determine the Source: Identify if the evidence resides in Konflux, Jira, or another system. | All Principles (Evidence Sourcing) | CRA Evidence Sourcing Plan | PSC | Q1 2026 | 2026-01-01 | 2026-03-31
Phase 1: Compliance Analysis and Prep | Documentation Analysis | 1. Gap analysis (how much of documentation already exists, what is the gap). 2. Define the centralized, internal and external documentation solution (Customer Portal, specialized hub) 3. Strategy for ensuring all documentation maintains consistent look and feel across all products. | All Principles (Transparency) | 1. Documentation Gap Analysis 2. Final Repository 3. Strategy for consistent look and feel (template) 4. List of applicable documents (wiki?) | PSC | Q2 2026 | 2026-04-01 | 2026-06-30
Phase 1: Compliance Analysis and Prep | Third party assessment vendors onboarded | Begin initial outreach to potential CRA vendors for potential assessors. | All Principles (External Validation) | Approved list of 3PAOs | PSC | Q3 2026 | 2026-07-01 | 2026-09-30
Phase 1: Compliance Analysis and Prep | Third party test labs onboarded | Begin initial outreach to potential test labs for potential assessors. (research extending Common Criteria relationships to include CRA). | All Principles (External Validation) | Approved list of test labs | PSC | Q3 2026 | 2026-07-01 | 2026-09-30
Phase 2: Automation and Tooling | Automation plan | Analyse and plan the automated evidence retrieval process (Konflux). How will the final system retrieve the evidence? Prioritize automation over manual retrieval for the vast majority of controls. | 1. Security by Design | Retrieval Automation Plan (maybe a diagram?) | PSC | Q2 2026 | 2026-04-01 | 2026-06-30
Phase 2: Automation and Tooling | Final Statement of Conformity Development | Create and vet the final Statement of Conformity (SoC) template to ensure legal compliance and consistent branding. | 1 & 2 (Compliance & Disclosure) | Standardized Statement of Conformity | PSC, Legal | Q2 2026 | 2026-04-01 | 2026-06-30
Phase 2: Automation and Tooling | Pilot Product Selection Target | Set a target date for selecting the initial easy-to-audit pilot product (e.g., uses Konflux, has good SDLC metrics, known team). | N/A (Project Governance) | Approved Target Pilot Selection Date | PSC | Q2 2026 | 2026-04-01 | 2026-06-30
Phase 3: Formal Adoption and Readiness | Pilot Internal Audit | 1.Conduct an internal audit on execution of the conformance delivery process on the selected pilot product. 2. Document lessons learned and conduct 2 more pilots. | All Principles (Independent Assurance) | Internal Audit Execution Plan | PSC | Q3 2026 Q4 2026 | 2026-10-01 | 2026-12-31
Phase 3: Formal Adoption and Readiness | Final Process Mandate | Obtain formal sign-off mandating the use of the new Conformance Delivery Process for all in-scope products. | 1. Security by Design (Management Approval) | Signed Conformance Delivery Process (V1.0) | PSC | Q4 2026 | 2026-10-01 | 2026-12-31